## Slide 1: From Data to Action: 30/60/90 Implementation plan
By: Apurva Bhave, Ph.D.

## Slide 2: Root-Cause Hypotheses (evidence-informed)
Middle-grades engagement (GR 7–8). Transitions, changing schedules, and weaker sense of belonging in early adolescence lead to sharp attendance dips. Advisory time is not consistently used for attendance nudges.
Targeted trust-building for Black/African American students. Families report communication that is more reactive than proactive; limited access to culturally responsive mentors and activities diminishes re-engagement.
Elementary logistics (TK–8). Irregular morning routines and transportation/housing instability drive late arrivals → full-day absences; parent work schedules complicate make-up work and follow-ups.
Service navigation. When students cross 3/6/9 absence thresholds, hand-offs between school, counseling, and services are inconsistent—interventions start late or stop early.
Use local artifacts (attendance logs, counselor notes, family outreach records) to ground these hypotheses.

## Slide 3: Bright Spots / What’s Working
Asian students (26.7%) show substantially lower chronic absence. Leverage strategies used by their schools (e.g., proactive teacher-family texting, attendance celebrations).
Male (50.0%) and English Learners (50.9%) are below All Students (61.4%)—borrow routines where EL family communication in home languages and positive attendance framing are already standard.
School exemplars. Identify the top two schools with the fastest improvement during the last quarter; document and scale their routines (bell-to-bell nudges, quick homeroom sweeps, same-day family contact).

## Slide 4: Risks & Dependencies
Data timeliness. Weekly SIS syncs and same-month cohort updates are required for accurate rates and early identification.
Small cohorts. With a 2024 cohort of 321, subgroup rates can swing quickly; show n on charts and suppress <10 to avoid over-interpreting noise.
Staffing capacity. 3/6/9 outreach and case management need clear owners (front office, AP, counselor) and back-up coverage.
Transportation & housing. Improvements depend on external partners (district ops, city agencies, CBOs); set MOUs for passes, routing, and emergency hotel stays.
Consistency & fidelity. Without a simple “playbook” and cadence, sites drift—track process indicators monthly (coverage, on-time check-ins).

## Slide 5: Equity & Privacy Note
Equity lens. All subgroup views are gap-to-All (percentage-point difference) to focus on disproportionality, not labels.
Privacy. Public, aggregated FSABD data; small-N suppression (<10) is applied; no PII in this report.
Governance. Reproducible pipeline (notebooks 01–03) and saved outputs under data/01_caldashboard/processed/. Any external data sharing follows district policy and FERPA.

## Slide 6: Recommendations (tied to your largest gaps)
GR 7–8 (gap +33.6 pp).
Action: Daily advisory “attendance minute” + 3/6/9 same-day outreach + weekly club/mentor invites.
Owner: MS AP + Counselors.
Monthly indicator: % 3/6/9 contacts on time; MS advisory completion rate (self-reported).
90-day target: −0.5 pp gap vs All.

## Slide 7: Recommendations (tied to your largest gaps)
Black/African American (gap +33.0 pp).
Action: Family ambassador program + culturally responsive activities; proactive texting in preferred channels; mentor check-ins twice/month.
Owner: Site Lead + Family Ambassadors.
Monthly indicator: % families reached; mentor check-ins completed.
90-day target: −0.5 pp gap vs All.

## Slide 8: Recommendations (tied to your largest gaps)
TK–8 span (gap +29.9 pp).
Action: Morning arrival sweeps + tardy-to-present conversion; “First-week reset” scripts; transportation pass referrals within 48 hours.
Owner: Elementary Principals + Student Services.
Monthly indicator: # tardy→present conversions; # transport referrals fulfilled.
90-day target: −0.5 pp gap vs All.

## Slide 9: Implementation & Monitoring (make it visual)
Metric (Monthly) | Owner | Target
% 3/6/9 check-ins completed on time | AP/Counselor | ≥ 90%
Family contact coverage (SMS/phone/email) | Front Office + Ambassadors | ≥ 85%
Tardy→Present conversions (elem) | Principal | +15% vs prior month
Advisory “attendance minute” completion (MS) | AP | ≥ 90%
Referrals fulfilled (transport/health) | Student Services | 100% of approved

## Slide 10: Site Rollout (Weeks 1–4) — San Francisco County Office of Education
Goal (30 days): Stand up Tier-1 & Tier-2 attendance routines; ≥85% contact; ≥90% 3/6/9 on-time; ≥0.5 pp improvement for focus subgroups.
Owner | Week 1 (Launch) | Week 2 (Operate) | Week 3 (Tighten) | Week 4 (Review & Adjust)
Principal / Site Lead | Kickoff; set targets; approve scripts; publish cadence (weekly stand-up + monthly share-out). | Run weekly stand-up; remove blockers; spotlight wins. | Share bright spots; address fidelity gaps. | 30-day review; update targets; board/cabinet note.
AP (Attendance Lead) | Build 3/6/9 rosters; train staff; start 'attendance minute' in advisory. | Daily 3/6/9 monitoring; ensure same-day outreach. | Classroom sweeps; tardy→present conversions; fidelity spot-checks. | Retrain weak spots; refresh rosters; plan next 30 days.
Attendance / Front Office | SIS cleanup; confirm contacts; load SMS lists; launch Tier-1 text/email. | Daily Tier-1 nudges; same-day calls for 2nd absence. | Chase unreachable families; update contacts. | Reconcile SIS; export contact & completion metrics.
Counselor / Case Manager | Review caseload; schedule check-ins for at-risk; prep care-team flow. | Start Tier-2 3/6/9 check-ins; log outcomes. | Escalate Tier-3; convene care team as needed. | Summarize student outcomes; handoffs for next cycle.
Family Ambassador / Liaison | Translate comms; verify preferred channels; host intro office hours. | Weekly office hours; feedback loop to AP. | Attendance celebration setup (recognition, incentives). | Quick pulse survey; report insights.
Student Services (Transportation/Health) | Fast-track transport referrals; hold clinic/telehealth blocks. | Fulfill passes within 48h; confirm appointments. | Fix routing issues; track utilization. | 30-day service report; close gaps.
EL Coordinator | Identify EL roster; home-language comms pack. | Start EL tutoring/incentives; track attendance. | Review session attendance; adjust schedule. | Set next-month targets & outreach.
SPED Lead / Case Managers | Attendance plan for top-risk students; parent outreach plan. | Case-manager cadence; document accommodations. | Verify follow-through; problem-solve barriers. | Update IEP teams with attendance status.
Data Lead | Baseline mini-dashboard (All + focus subgroups). | First weekly update: coverage, 3/6/9 completion. | Add gap-to-All view; call out bright spots. | 30-day report; next-month targets.
Track weekly: % 3/6/9 on-time; family contact coverage; tardy→present conversions; transport referrals fulfilled; subgroup gap vs All | Cadence: Monthly KPI update; biweekly 3/6/9 review; quarterly gap review & pivots | Targets (30 days): All Students −0.5 pp; each focus subgroup gap −0.5 pp; ≥90% 3/6/9 on-time; ≥85% family contact coverage

## Slide 11: Site Rollout (Weeks 1–4) — Burbank Unified
Goal (30 days): Same cadence; prioritize middle grades + top-gap subgroups; ≥85% contact; ≥90% 3/6/9 on-time; ≥0.5 pp gap reduction.
Owner | Week 1 (Launch) | Week 2 (Operate) | Week 3 (Tighten) | Week 4 (Review & Adjust)
Principal / Site Lead | Kickoff; targets; scripts; cadence. | Weekly stand-up; unblock. | Share bright spots; address gaps. | 30-day review; update plan; share-out.
AP (Attendance Lead) | 3/6/9 rosters; staff training; advisory 'attendance minute.' | Daily monitoring; same-day outreach. | Hall sweeps; tardy→present; fidelity checks. | Retrain; refresh rosters; next cycle.
Attendance / Front Office | SIS cleanup; contact verification; start Tier-1 SMS/email. | Daily nudges; second-day absence calls. | Contact hygiene; reach hard-to-reach. | Reconcile & export metrics.
Counselor / Case Manager | Caseload review; schedule Tier-2. | Tier-2 check-ins begin; log outcomes. | Escalate Tier-3; care-team mtg. | Outcome summary; handoffs.
Family Liaison | Translate; confirm channels; intro office hours. | Weekly hours; feedback loop. | Recognition events. | Family pulse survey.
Student Services | Transport referral queue + clinic blocks. | 48h fulfillment SLA. | Routing fixes; utilization. | 30-day service report.
EL Coordinator | EL roster; home-language comms. | Tutoring/incentives start; track. | Attendance review; adjust. | Next-month plan.
SPED Lead | Plan for top-risk SPED students. | Case-manager cadence & family contact. | Barrier solving; verify supports. | IEP updates on attendance.
Data Lead | Baseline dashboard (All + focus). | Weekly update: coverage & completion. | Add gap view; highlight wins. | 30-day report & targets.
Track weekly: % 3/6/9 on-time; family contact coverage; tardy→present conversions; transport referrals fulfilled; subgroup gap vs All | Cadence: Monthly KPI update; biweekly 3/6/9 review; quarterly gap review & pivots | Targets (30 days): All Students −0.5 pp; each focus subgroup gap −0.5 pp; ≥90% 3/6/9 on-time; ≥85% family contact coverage

## Slide 12: Appendix (Data & Methods) – add two clarifiers
Rate math: chronic_absent_rate = chronic_absent_count / cohort (rates shown as % in visuals).
Suppression rule: no rate displayed when cohort < 10 to protect privacy; footnote charts accordingly.
Reproducibility: paths:
data/01_caldashboard/processed/kpi_chronic_wide_all_levels.csv
projects/01_california-dashboard-replica/assets/*.png